PRIVILEGED & CONFIDENTIAL — ATTORNEY WORK PRODUCT — DRAFT FOR PARTNER REVIEW

PPA DEVIATION REPORT

Prairie Crest Wind Project (250 MW, Osage County, Oklahoma)

Executed Power Purchase Agreement (Feb. 4, 2025) compared against Binding Term Sheet (Nov. 8, 2024) and Negotiation Summary (Jan. 22, 2025), with Financial Close Risk Assessment against the Ridgeline Tax Equity Due Diligence Checklist

| To | Catherine Ainsworth, Ryan Matsuda — Thornfield & Marsh LLP (counsel to Seller) |
| --- | --- |
| Client | Crescent Ridge Wind Partners LLC (Seller), a wholly owned subsidiary of Verdana Renewable Holdings Inc. |
| Counterparty | Lakeshore Municipal Electric Authority (Buyer); Buyer’s counsel Prescott & Hale LLP (Jeffrey Langdon) |
| Use | Responds to Tax Equity DD Checklist Item 12 (PPA deviation analysis) and cross-referenced Items 15, 16, 18, 22, 30, 31, 34, 37, 40, 43, 44. Deviation report due to Ridgeline Capital Partners (Priya Venkataraman) by March 14, 2025; target financial close April 15, 2025 (Ridgeline $116.25M tax equity; Elkhorn Infrastructure Credit $232.5M construction/term loan). |
| Distribution note | This draft contains candid internal assessments (including of the negotiation record). A Ridgeline-facing version should be derived from Sections 3, 4 and 6 after partner review; Section 5 commentary on negotiating leverage should not be forwarded. |

# 1. Executive Summary

Bottom line. The executed PPA does not conform to the Binding Term Sheet in all material respects, and Checklist Item 12 cannot be answered “consistent.” We identified 26 deviations plus a set of ancillary drafting inconsistencies. Only two (the 75% performance guarantee threshold and the 50% shortfall LD rate) are deviations Seller actually agreed to; two more (excess-REC retention and March 1, 2026 early COD) were still “being discussed” as of January 22 and appear in the executed PPA without any confirmed agreement trail. Every other deviation is either contrary to positions Seller expressly held in negotiations or a new term the Term Sheet did not contemplate, and nearly all of them cut against Seller.

Financial close risk: RED (high). As executed, the PPA will not support an April 15, 2025 close with Ridgeline. Three issues are, in our view, independently close-blocking:

Tax equity excluded from “Financing Party” (D-1/D-2). Exhibit A limits “Financing Party” to senior secured lenders and their agents; Exhibit H §8 goes further and expressly states that any assignment to a “tax equity investor, partnership-flip partner, or similar equity investor” requires Buyer consent under §17.1(b). Ridgeline therefore has no consent-free collateral assignment, cure, step-in or replacement-PPA rights. Ms. Kowalski’s summary records Ridgeline’s position that this is non-negotiable (“Ridgeline won’t close”). This is directly contrary to Term Sheet §1 and §15.1 and to Mr. Langdon’s January 17 assurance.

Admitting Ridgeline as a member may itself breach the PPA (D-3). The partnership-flip requires amending and restating Seller’s LLC Agreement (Checklist Item 2). PPA §17.1(b) requires Buyer consent for any “change of control of Seller” (Term Sheet §15.3 required notice only), and Seller’s §11.1(g) representation that “no other Person holds any ownership interest in Seller” is deemed repeated at COD — a false repetition is an Event of Default under §18.1(b). Without a fix, the flip structure itself creates default exposure.

Exhibit B price table does not tie to the 1.5% escalator (D-4). Exhibit B is built on an approximately 2.0% escalator (Year 6 $39.27 vs. $39.08 under the formula; Year 20 $51.80 vs. $48.13). At the Contract Quantity the table overstates Years 6–20 revenue by ~$23.18 million nominal (~$9.58 million PV at 6%). Section 4.2(a) says prices “shall be as set forth in” Exhibit B while §4.2(b) states the formula and §1.3 makes the body control — an internal conflict that Ridgeline’s model (Item 40) and Elkhorn’s base case cannot underwrite. The table must be corrected by amendment.

Several further deviations will be treated by Ridgeline/Elkhorn as material even if not individually close-blocking: litigation in Osage County District Court instead of confidential AAA arbitration (D-11; Item 43); omission of the Buyer-bears-100% new-transmission-charge carve-out (D-10; Item 22); economic curtailment compensation at 80% rather than 90% (D-5); Delay LDs of $175,000/month capped at $2.5M rather than $125,000/month capped at $1.5M (D-6), combined with an evergreen Outside Date and Event-of-Default/termination-damages exposure that eliminates the Term Sheet’s sole-remedy construct (D-7); a 12-month (not 18-month) force majeure termination right (D-8); Availability LDs at $65,000 (not $50,000) per point and outside the 20% combined LD cap (D-12/D-13); and a performance bond due within 30 days of the Effective Date (i.e., by March 6, 2025) with no step-down (D-21/D-22).

Why this cannot be fixed by pointing to the Term Sheet. PPA §20.3 supersedes the Term Sheet “to the extent inconsistent,” the PPA recitals say the same, and Term Sheet §18.5 itself provides that the Definitive PPA controls in any conflict (the Term Sheet survives only as an aid to interpreting genuine ambiguity). The Term Sheet is therefore useful for D-4 (where the PPA is internally ambiguous) but not for the clear textual deviations. Each must be remedied by a written amendment signed by both Parties (§20.4), which for Buyer will likely require Board of Trustees action and compliance with public-meeting requirements (§11.2(b), (g)). That process is the critical path to April 15.

Recommended path. Open a single “First Amendment to PPA” package with Prescott & Hale immediately (target delivery of draft by March 7, 2025), anchored on (i) the Financing Party / Exhibit H / change-of-control / §11.1(g) fixes and (ii) restoring the Term Sheet terms for each non-agreed deviation. Seller holds real currency for the trade: correcting Exhibit B to the 1.5% formula is worth ~$23.2 million nominal to Buyer, and Seller can offer to document the agreed quarterly generation reports. In parallel, deliver this report (Ridgeline version) to Ridgeline on or before March 14 with the remediation plan, and confirm the performance bond is (or will be) delivered by March 6 to avoid an independent compliance problem. See Section 7.

# 2. Scope, Documents and Method

Documents reviewed in full:

Binding Term Sheet dated November 8, 2024, Seller/Buyer, 18 sections plus Annex A (Indicative Contract Price Schedule) (the “Term Sheet” or “TS”).

Power Purchase Agreement dated as of February 4, 2025, prepared by Prescott & Hale LLP, Articles 1–20 and Exhibits A–H (the “PPA”).

Email from Dana Kowalski (Verdana) to Catherine Ainsworth, cc Ryan Matsuda and Marcus Ellington, dated January 22, 2025, “Re: Prairie Crest PPA — Negotiation Summary and Open Items” (the “Negotiation Summary”).

Ridgeline Tax Equity Due Diligence Checklist (45 items) and Status Tracker (the “Checklist”).

Method: clause-by-clause comparison of every Term Sheet commercial term against the PPA body and exhibits; each difference classified by negotiation status (using the Negotiation Summary as the only record of agreement), direction of impact on Seller/financing parties, and severity for financial close; and mapped to the relevant Checklist item. Figures were recomputed independently (price tables, LD and curtailment exposure).

Classification key:

| Status code | Meaning |
| --- | --- |
| AGREED | Departure Seller agreed to in negotiations (per Negotiation Summary §1). Not documented by Term Sheet amendment or side letter. |
| OPEN-IN PPA | Item listed as “still being discussed” in Negotiation Summary §4 that nonetheless appears in executed PPA; agreement trail must be confirmed. |
| NOT AGREED | Contrary to a term Seller expressly said must track the Term Sheet (Negotiation Summary §2–§3), or otherwise not agreed. |
| NEW TERM | PPA provision with no Term Sheet counterpart that changes the commercial risk allocation. |
| DRAFTING | Internal inconsistency, arithmetic or factual error. |

Severity: Critical = close-blocking for Ridgeline absent cure; High = material to Ridgeline/Elkhorn underwriting and should be fixed pre-close; Medium = should be fixed or expressly disclosed/accepted; Low = disclosure or clean-up.

# 3. Deviation Register (Summary)

All 26 deviations, ordered by significance to financial close. Detailed analysis follows in Section 4.

| # | Issue | Term Sheet | PPA | Status | Effect on Seller | Severity | Checklist |
| --- | --- | --- | --- | --- | --- | --- | --- |
| D-1 | “Financing Party” excludes tax equity; consent-free collateral assignment limited to lenders | TS §1 (“Financing Parties”), §15.1 | PPA Ex. A (“Financing Party”), §17.1(a), §17.1(b), Ex. H Recitals B–C and §8 | NOT AGREED | Adverse to Seller and Ridgeline | Critical | 12(vi), 18(a)–(c), 30, 31 |
| D-2 | Cure, step-in and replacement-PPA rights unavailable to tax equity | TS §15.1 | PPA §17.3, §18.4, §20.9, Ex. H §§3–6 | NOT AGREED | Adverse | Critical | 31(a)–(c), 29, 30 |
| D-3 | Change of control requires Buyer consent; sole-ownership representation conflicts with partnership flip | TS §15.3 | PPA §17.1(b), §11.1(g), §11.1 (repetition at COD), §18.1(b) | NOT AGREED | Adverse | High | 2, 18, 19, 45 |
| D-4 | Exhibit B price table built on ~2.0% escalation, not 1.5% | TS §5.2–5.6, Annex A | PPA §4.2(a), §4.2(b), §1.3, Ex. B Parts 1–3 | NOT AGREED (DRAFTING) | Facially Seller-favorable but unbankable; dispute risk | High | 12(i), 15, 40 |
| D-5 | Economic curtailment compensated at 80% (not 90%) of Contract Price | TS §6.1–6.3 | PPA §6.1(a), §6.2(a), §6.4 | NOT AGREED | Adverse | High | 12(iv), 40 |
| D-6 | Delay LDs increased to $175,000/month, cap $2.5M | TS §7.1–7.2 | PPA §3.5(b)–(c); Ex. G Note 2 | NOT AGREED | Adverse | High | 12(iii), 34 |
| D-7 | Outside Date: evergreen extension, Event of Default and termination damages erode sole-remedy construct | TS §3.5, §7.1, §7.3 | PPA §3.5(a), (c), (d); §3.6; §18.1(a); §18.3(b); Ex. G Note 3 | NOT AGREED / NEW TERM | Adverse | High | 12(iii), 34 |
| D-8 | Force majeure termination after 12 months (not 18), on 60 days’ notice | TS §14.4 | PPA §12.4 | NOT AGREED | Adverse | High | 12(v) |
| D-9 | Force majeure definition and conditions narrowed | TS §14.1–14.3 | PPA §12.1–12.3 | NOT AGREED | Mixed, net adverse | Medium | 12(v) |
| D-10 | Change of law: Buyer-bears-100% new transmission charges carve-out omitted | TS §13.1–13.2 | PPA §14.1–14.2; §5.2; §5.3 | NOT AGREED | Adverse | High | 22, 12 |
| D-11 | Dispute resolution: litigation in Osage County District Court instead of mediation + AAA arbitration | TS §17.1–17.5 | PPA §19.1–19.4 | NOT AGREED | Adverse | High | 43, 12(vii) |
| D-12 | Mechanical Availability LD rate $65,000 (not $50,000) per percentage point | TS §9.1–9.3 | PPA §8.7; Ex. C §3 | NOT AGREED | Adverse | Medium | 37, 12(ii) |
| D-13 | 20% annual LD cap no longer covers Availability LDs | TS §9.4 | PPA §8.5, §8.7 | NOT AGREED | Adverse | Medium | 12(ii), 40 |
| D-14 | Performance LDs no longer a clean sole remedy | TS §8.4 | PPA §8.1 (last sentence), §8.5 | NOT AGREED / NEW TERM | Adverse | Medium | 12(ii) |
| D-15 | Minimum Annual Energy Production reduced to 75% of CQ (637,500 MWh) | TS §8.1 | PPA §8.3; Ex. A (“MAEP”) | AGREED | Seller-favorable | Low | 12(ii) |
| D-16 | Shortfall LD rate reduced to 50% of Contract Price | TS §8.2–8.3 | PPA §8.4 | AGREED | Seller-favorable | Low | 12(ii) |
| D-17 | Quarterly generation reporting (consideration for D-15/D-16) not reflected | N/A (consideration for agreed deviations) | PPA §3.4 (construction progress only), §7.3 (monthly meter data) | DRAFTING (documentation gap) | Neutral; evidentiary | Low | 12(ii) |
| D-18 | Excess-generation RECs retained by Seller | TS §10.1, §10.3 | PPA §10.1, §10.2; §8.6 | OPEN-IN PPA | Seller-favorable | Medium | 12(viii) |
| D-19 | REC scope limited to delivered energy; tracking registry | TS §10.1–10.2 | PPA §10.1–10.2; Ex. A (“REC”) | NEW TERM | Neutral | Low | 12(viii) |
| D-20 | Early COD permitted from March 1, 2026 | TS §3.4 | PPA §3.3; Ex. G | OPEN-IN PPA | Seller-favorable | Low | 34, 12 |
| D-21 | Performance bond due within 30 days of Effective Date (not 30 days before construction) | TS §11.1–11.2, §11.4 | PPA §13.1; §2.4(a); Ex. F §2 | NOT AGREED | Adverse | Medium | 16 |
| D-22 | Bond step-down omitted; bond covers all obligations for full Term on demand | TS §11.3 | PPA §13.1; Ex. F §§1–3 | NOT AGREED | Adverse | Medium | 16, 28 |
| D-23 | COD conditions: 240 MW capacity test and Buyer confirmation process | TS §1 (“COD”), §3 | PPA §3.2(i)–(vi); Ex. A (“Commercial Operation Date”); Ex. C §1 | NEW TERM | Adverse | Medium | 34, 36 |
| D-24 | Buyer credit support conditional; downgrade collateral | TS §12.1–12.2 | PPA §13.2, §13.3; §2.3(e) | NEW TERM | Seller-favorable | Low | 13 |
| D-25 | Termination damages formula and aggregate liability cap | No TS counterpart (TS §3.5, §7.3, §8.4 sole remedies) | PPA §18.3(b); §16.2; §16.3 | NEW TERM | Adverse / ambiguous | Medium | 12, 40 |
| D-26 | Assignment mechanics: Buyer conditions and Buyer assignment | TS §15.2 | PPA §17.1(b) conditions; §17.2 | NEW TERM | Adverse (moderate) | Low | 18(c) |

Totals by severity: Critical 2; High 8; Medium 9; Low 7.  By status: NOT AGREED 13; NOT AGREED (DRAFTING) 1; NOT AGREED / NEW TERM 2; AGREED 2; DRAFTING (documentation gap) 1; OPEN-IN PPA 2; NEW TERM 5.

# 4. Detailed Deviation Analysis

## 4.1 Financing, assignment and tax equity

### D-1  “Financing Party” excludes tax equity; consent-free collateral assignment limited to lenders

| References | TS: TS §1 (“Financing Parties”), §15.1 ¦ PPA: PPA Ex. A (“Financing Party”), §17.1(a), §17.1(b), Ex. H Recitals B–C and §8 |
| --- | --- |
| Term Sheet | “Financing Parties” = senior secured lenders AND “tax equity investors providing equity financing.” Seller may collaterally assign to Financing Parties “(including senior secured lenders and tax equity investors)” without Buyer consent; Buyer must deliver a consent with step-in/cure rights “at no cost to Buyer”; that obligation is a “material covenant.” |
| Executed PPA | “Financing Party” = “any senior secured lender providing construction financing or term debt financing … and any trustee or agent acting on behalf of such lenders.” Tax equity omitted. Collateral assignment to any non-Financing Party requires Buyer consent (§17.1(b)), which Buyer may condition on technical capability, creditworthiness and replacement credit support. Ex. H §8: assignment to “any tax equity investor, partnership-flip partner, or similar equity investor” requires Buyer’s prior written consent. “No cost to Buyer” and “material covenant” language dropped; new 15-Business-Day post-assignment notice with copy of the collateral assignment. |
| Status / effect / severity | NOT AGREED ¦ Adverse to Seller and Ridgeline ¦ Critical ¦ Checklist Item(s) 12(vi), 18(a)–(c), 30, 31 |
| Negotiation record | Negotiation Summary §3: raised with Mr. Langdon on the January 17 call; he “confirmed that Prescott & Hale would define ‘Financing Parties’ broadly enough to include tax equity investors in a partnership-flip structure.” Ridgeline’s January 10 commitment letter makes consent-free collateral assignment and step-in rights non-negotiable. The executed PPA reflects the opposite, and Ex. H §8 affirmatively carves tax equity out — this was not a drafting oversight that a court would likely cure by construction. |
| Impact | Answers to Checklist Item 18: (a) No — limited to senior secured lenders/agents; (b) No — §17.1(a) consent-free right runs only to that narrow class; (c) Yes — §17.1(b) requires Buyer consent, subject to a “not unreasonably withheld, conditioned, or delayed” standard but with express permissive conditions (technical capability, creditworthiness ≥ Seller, replacement credit support) that give Buyer leverage. Per Negotiation Summary, Ridgeline will not close on this basis. The Checklist also flags the point as relevant to Ridgeline’s tax position under Rev. Proc. 2007-65 (as modified); tax counsel should confirm the precise safe-harbor consequence, but the commercial consequence (no close) does not depend on it. |
| Recommendation | First Amendment: (1) redefine “Financing Party” to include any lender, tax equity investor (including any partnership-flip investor or class of membership interests in Seller or any upstream owner), lessor, or agent/trustee for any of them, mirroring TS §1; (2) conform §17.1(a), §17.3, §18.4, §20.9; (3) delete Ex. H §8 second and third sentences and revise Ex. H so it can be executed in favor of Ridgeline (a tax-equity-specific consent form or a form usable by “Financing Party” generally); (4) reinstate “at no cost to Buyer” and “material covenant.” Fallback if Buyer refuses to amend the definition before April 15: a direct Buyer consent and estoppel in favor of Ridgeline executed at close, expressly granting §17.3 rights — only if Ridgeline confirms that is acceptable. |

### D-2  Cure, step-in and replacement-PPA rights unavailable to tax equity

| References | TS: TS §15.1 ¦ PPA: PPA §17.3, §18.4, §20.9, Ex. H §§3–6 |
| --- | --- |
| Term Sheet | Financing Parties (expressly including tax equity) receive “customary step-in rights, cure rights, and other lender or investor protections.” |
| Executed PPA | 180-day additional cure, step-in, replacement PPA and default-notice rights run to “Financing Parties” only (i.e., lenders); Ex. H is drafted for a lender “Agent” under a “credit agreement.” Third-party-beneficiary status (§20.9) likewise limited. |
| Status / effect / severity | NOT AGREED ¦ Adverse ¦ Critical ¦ Checklist Item(s) 31(a)–(c), 29, 30 |
| Negotiation record | Consequence of D-1; same negotiation history. |
| Impact | Ridgeline would have no contractual right to receive default notices, cure, or step in on a Seller default (e.g., a performance bond failure or flip-related representation breach). Elkhorn’s rights are intact, so the intercreditor (Item 29) would be negotiated with only the lender holding PPA protections — a structural imbalance Ridgeline will not accept. |
| Recommendation | Cured by D-1 amendment; additionally, provide that Buyer will deliver notices to each Financing Party identified by Seller and will recognize priority as agreed among Financing Parties in their intercreditor arrangements. |

### D-3  Change of control requires Buyer consent; sole-ownership representation conflicts with partnership flip

| References | TS: TS §15.3 ¦ PPA: PPA §17.1(b), §11.1(g), §11.1 (repetition at COD), §18.1(b) |
| --- | --- |
| Term Sheet | Change of control of Seller is NOT an assignment requiring consent, provided 30 days’ prior notice and written assumption by the surviving/acquiring entity. |
| Executed PPA | Any assignment “in connection with … a change of control of Seller” requires Buyer consent (not unreasonably withheld), with Buyer’s conditions. “Change of control” is undefined. Seller represents (repeated at COD) that it is wholly owned by Verdana and “no other Person holds any ownership interest in Seller”; a materially false repetition is an Event of Default (§18.1(b)) with no cure period. |
| Status / effect / severity | NOT AGREED ¦ Adverse ¦ High (Critical in combination with D-1) ¦ Checklist Item(s) 2, 18, 19, 45 |
| Negotiation record | Not addressed in Negotiation Summary; the Term Sheet position was settled. |
| Impact | The flip requires Seller’s LLC Agreement to be amended/restated to admit Ridgeline (Checklist Item 2). Admission of Ridgeline before COD (expected June 1, 2026) will make the §11.1(g) representation untrue when repeated at COD, and Buyer may argue the admission (and any later flip or Verdana sale) is a “change of control” requiring consent. This also complicates the bring-down certificate (Item 45). |
| Recommendation | Amend §17.1(b) to restore TS §15.3 (notice-only for change of control) and expressly provide that (i) admission of, and transfers among, tax equity investors and the occurrence of any allocation “flip” and (ii) any foreclosure/transfer to a Financing Party are not assignments or changes of control requiring consent. Amend §11.1(g) to permit ownership by Verdana and Financing Parties (or limit the representation to the Effective Date). |

### D-26  Assignment mechanics: Buyer conditions and Buyer assignment

| References | TS: TS §15.2 ¦ PPA: PPA §17.1(b) conditions; §17.2 |
| --- | --- |
| Term Sheet | Full assignment by either Party requires consent not unreasonably withheld, conditioned or delayed. |
| Executed PPA | Seller assignments: consent not unreasonably withheld but Buyer may condition on technical capability, creditworthiness ≥ Seller and replacement credit support; Seller not released until assumption acceptable to Buyer. Buyer may assign without consent to a successor municipal entity with equivalent rating or acceptable credit support. |
| Status / effect / severity | NEW TERM ¦ Adverse (moderate) ¦ Low ¦ Checklist Item(s) 18(c) |
| Negotiation record | Not discussed. |
| Impact | Expands Buyer’s consent leverage on any Facility sale or Verdana-level transaction; Buyer’s consent-free successor assignment is customary. |
| Recommendation | Address with D-1/D-3 amendments; otherwise disclose. |

## 4.2 Pricing and revenue

### D-4  Exhibit B price table built on ~2.0% escalation, not 1.5%

| References | TS: TS §5.2–5.6, Annex A ¦ PPA: PPA §4.2(a), §4.2(b), §1.3, Ex. B Parts 1–3 |
| --- | --- |
| Term Sheet | $38.50/MWh fixed for CY1–5; 1.5% compounding from CY6: P(N) = $38.50 × 1.015^(N–5), rounded to cent. CY6 $39.08 … CY20 $48.11 (Annex A). |
| Executed PPA | Body text and Ex. B Part 1 recite 1.5% and the same formula, but Ex. B Part 2 table shows CY6 $39.27 … CY20 $51.80 (consistent with 2.0% compounding, with additional anomalies in CY14, CY15 and CY20). Ex. B Part 3 sample CY6 revenue $33,379,500 (TS Annex A: $33,218,000). §4.2(a) states prices “shall be as set forth in the price table in Exhibit B”; §4.2(b) points discrepancies to §1.3 (body controls). |
| Status / effect / severity | NOT AGREED (DRAFTING) ¦ Facially Seller-favorable but unbankable; dispute risk ¦ High ¦ Checklist Item(s) 12(i), 15, 40 |
| Negotiation record | Negotiation Summary §2: escalation “was not discussed as a point of negotiation — both sides accepted the term sheet pricing formula.” Ms. Kowalski specifically asked that Exhibit B be tied out to 1.5%. |
| Impact | Overstatement vs. formula at Contract Quantity: ~$0.19/MWh in CY6 rising to ~$3.67/MWh in CY20; ~$23.18M nominal over CY6–20 (~$9.58M PV at 6%), ~3.2% of total contract revenue. Under §1.3 the body (formula) should prevail, and TS §18.5 permits use of the Term Sheet to resolve ambiguity — so the higher table prices are unlikely to be enforceable and would invite a billing dispute (and, as drafted, Osage County litigation). Ridgeline’s model must use 1.5% (Item 40); Elkhorn will size debt on the formula. Leaving the conflict in place is a diligence finding in itself. See Schedule 1. |
| Recommendation | Replace Ex. B Part 2 and Part 3 with formula-derived values (Schedule 1, column “Formula”) and delete the “shall be as set forth in the price table” clause or make the formula expressly control. Note that TS Annex A itself contains $0.01–$0.02 rounding variances from its own formula (CY7 and CY9–20); use formula values, not Annex A. |

### D-5  Economic curtailment compensated at 80% (not 90%) of Contract Price

| References | TS: TS §6.1–6.3 ¦ PPA: PPA §6.1(a), §6.2(a), §6.4 |
| --- | --- |
| Term Sheet | 90% of then-applicable Contract Price per curtailed MWh; cap 5% of CQ (42,500 MWh/CY). Covers curtailment by Buyer or Buyer’s balancing authority “acting at Buyer’s direction or for Buyer’s economic benefit.” |
| Executed PPA | 80% of Contract Price; cap 42,500 MWh/CY (conforms). Definition limited to curtailment “initiated at the direction of Buyer or Buyer’s designee.” Seller need not accept uncompensated economic curtailment above cap (Seller-favorable addition). |
| Status / effect / severity | NOT AGREED ¦ Adverse ¦ High ¦ Checklist Item(s) 12(iv), 40 |
| Negotiation record | Negotiation Summary §2: Mr. Langdon floated 80% in his first markup; Seller “pushed back” and Ms. Kowalski believed Ms. Nouri confirmed Buyer would hold at 90%. The executed text reflects Buyer’s rejected markup. |
| Impact | At the cap: $163,625 lost in CY1 (42,500 × $38.50 × 10%), ~$3.59M over the Term (formula prices). The narrower definition drops curtailment “for Buyer’s economic benefit,” which could leave some balancing-authority curtailments uncompensated. |
| Recommendation | Restore 90% and the TS §6.1 “or for Buyer’s economic benefit” formulation; keep the favorable §6.4 last sentence and §8.2(d). |

### D-18  Excess-generation RECs retained by Seller

| References | TS: TS §10.1, §10.3 ¦ PPA: PPA §10.1, §10.2; §8.6 |
| --- | --- |
| Term Sheet | ALL RECs from every MWh generated during the Term transfer to Buyer, bundled, whether delivered at, above or below CQ; Seller has no interest in any REC. |
| Executed PPA | RECs on Net Energy Output above 100% of CQ in a Contract Year are retained by Seller, who may sell them; monthly transfers to Buyer “up to the Contract Quantity, on a cumulative annual basis.” Buyer still buys all excess energy at the full (bundled) Contract Price (§8.6). |
| Status / effect / severity | OPEN-IN PPA ¦ Seller-favorable ¦ Medium (documentation/ambiguity) ¦ Checklist Item(s) 12(viii) |
| Negotiation record | Negotiation Summary §4: raised by Tamara Nouri; “still being discussed”; Seller inclined to accept “if they offer it,” and asked that the bundled/unbundled boundary be cleanly drafted. No record of final agreement before execution. |
| Impact | Upside for Seller (P50 876,000 MWh implies ~26,000 excess RECs/yr). Risks: (i) Buyer pays the bundled price for excess energy that no longer carries RECs — Buyer may later argue mistake or seek a price reduction for excess MWh; (ii) month-by-month allocation versus annual true-up is not fully specified (e.g., RECs already transferred in a year where output later falls short, or partial first/last CY proration under §8.8); (iii) M-RETS vintage/serial number allocation mechanics are absent. |
| Recommendation | Confirm agreement status with Buyer in writing; add mechanics (annual true-up, serial-number allocation, proration) and consider an express excess-energy price (or confirm full price) to foreclose a later challenge. Disclose to Ridgeline as a deviation (Item 12(viii)). |

### D-19  REC scope limited to delivered energy; tracking registry

| References | TS: TS §10.1–10.2 ¦ PPA: PPA §10.1–10.2; Ex. A (“REC”) |
| --- | --- |
| Term Sheet | “All RECs” includes RECs attributable to energy curtailed, spilled or not delivered; registration via SPP’s environmental attribute tracking system (or successor). |
| Executed PPA | Transfer limited to RECs associated with Net Energy Output delivered; registration with M-RETS (or successor designated by Buyer). |
| Status / effect / severity | NEW TERM ¦ Neutral ¦ Low ¦ Checklist Item(s) 12(viii) |
| Negotiation record | Not discussed. |
| Impact | Practical effect limited (undelivered MWh generally create no RECs), and M-RETS is the market-standard registry for SPP-region wind. Note for completeness only. |
| Recommendation | No action other than disclosure. |

## 4.3 COD, delay and termination

### D-6  Delay LDs increased to $175,000/month, cap $2.5M

| References | TS: TS §7.1–7.2 ¦ PPA: PPA §3.5(b)–(c); Ex. G Note 2 |
| --- | --- |
| Term Sheet | $125,000/month (pro rata), capped at 12 months = $1,500,000. |
| Executed PPA | $175,000/month (pro rata), aggregate cap $2,500,000 (reached after ~14.3 months). |
| Status / effect / severity | NOT AGREED ¦ Adverse ¦ High ¦ Checklist Item(s) 12(iii), 34 |
| Negotiation record | Negotiation Summary §2: Delay LDs “should carry over from the term sheet as-is. We didn’t negotiate any changes here.” |
| Impact | Maximum exposure +$1.0M (+67%); at 12 months of delay $2.1M vs. $1.5M. Combined with D-7, LDs can continue accruing after the Outside Date. Relevant to EPC delay-LD back-to-back (Item 9) and sources/uses contingency. |
| Recommendation | Restore $125,000/month and a $1.5M (12-month) cap; conform Ex. G Note 2. |

### D-7  Outside Date: evergreen extension, Event of Default and termination damages erode sole-remedy construct

| References | TS: TS §3.5, §7.1, §7.3 ¦ PPA: PPA §3.5(a), (c), (d); §3.6; §18.1(a); §18.3(b); Ex. G Note 3 |
| --- | --- |
| Term Sheet | If no COD by Sept. 1, 2027, either Party may terminate by notice within 30 days, “without further liability … except for any accrued and unpaid delay liquidated damages.” Delay LDs (plus that termination right) are Buyer’s sole and exclusive remedy for delay. |
| Executed PPA | Same Outside Date, but (i) Outside Date auto-extends in successive 90-day periods if no notice within 90 days (§3.6); (ii) Delay LDs accrue until COD or a §3.6 termination, so they continue past Sept. 1, 2027 until the cap; (iii) §3.5(c) says reaching the cap does not relieve Seller of its obligation to achieve COD by the Outside Date; (iv) failure to achieve COD by the Outside Date is a Seller Event of Default (§18.1(a)), opening §18.3(b) termination damages and a draw on the $7.5M bond (Ex. F). |
| Status / effect / severity | NOT AGREED / NEW TERM ¦ Adverse ¦ High ¦ Checklist Item(s) 12(iii), 34 |
| Negotiation record | Not specifically discussed; the Term Sheet’s sole-remedy and no-further-liability construct was settled. |
| Impact | Converts a capped, liquidated delay exposure into potential uncapped expectation damages (subject only to the §16.3 cap, which equals aggregate contract revenue, ~$718M — effectively no cap). §18.1(a) also refers to “extension for Force Majeure events as provided in this Agreement,” but no provision actually extends the Guaranteed COD or Outside Date for FM (§12.3 and Ex. G Note 6 point back to §3.5, which contains none) — an ambiguity adverse to Seller. |
| Recommendation | Delete §18.1(a) (or make the §3.6 termination the exclusive remedy, with no termination damages); restore TS §3.5 notice window; limit Delay LD accrual to the Outside Date; add express day-for-day FM extension of Guaranteed COD and Outside Date (capped) to fill the gap. |

### D-20  Early COD permitted from March 1, 2026

| References | TS: TS §3.4 ¦ PPA: PPA §3.3; Ex. G |
| --- | --- |
| Term Sheet | Seller may achieve COD up to 3 months before Guaranteed COD (i.e., as early as June 1, 2026) on 60 days’ notice; Buyer to use commercially reasonable efforts to accept. |
| Executed PPA | Seller may declare COD as early as March 1, 2026 on 60 days’ notice, if all §3.2 conditions satisfied; Contract Year 1 and the Term run from actual COD; Buyer to “cooperate in good faith.” |
| Status / effect / severity | OPEN-IN PPA ¦ Seller-favorable ¦ Low ¦ Checklist Item(s) 34, 12 |
| Negotiation record | Negotiation Summary §4: “Lakeshore is fine with” March 1, 2026; listed as still under discussion. |
| Impact | Scheduling flexibility; an earlier COD also starts the 5-year fixed-price period and later escalation earlier. Interacts with D-23 (Buyer’s 10-BD COD review) and Ex. G milestones (turbine delivery complete Jan. 31, 2026). |
| Recommendation | Disclose as agreed improvement; obtain Buyer acknowledgment in the First Amendment. |

### D-23  COD conditions: 240 MW capacity test and Buyer confirmation process

| References | TS: TS §1 (“COD”), §3 ¦ PPA: PPA §3.2(i)–(vi); Ex. A (“Commercial Operation Date”); Ex. C §1 |
| --- | --- |
| Term Sheet | COD per Section 3 requirements (no capacity test or Buyer acceptance specified). |
| Executed PPA | COD requires a capacity test of ≥240 MW (96% of 250 MW nameplate), LGIA in effect, all permits, metering certified, COD Notice and a ≥10-Business-Day Buyer review/objection period; COD defined by reference to Buyer’s acceptance or deemed acceptance. |
| Status / effect / severity | NEW TERM ¦ Adverse ¦ Medium ¦ Checklist Item(s) 34, 36 |
| Negotiation record | Not discussed. |
| Impact | Ex. C states installed capacity is 62 × 4.0 MW = 248 MW, so the 240 MW test effectively requires 60 of 62 turbines on test day; the Buyer review period can push COD past Sept. 1, 2026 and trigger Delay LDs even where the Facility is complete. Item 36 (COD testing protocol) must be built to this definition; EPC substantial completion tests should be aligned. |
| Recommendation | Make COD effective as of the date of the COD Notice if confirmed (relation-back); limit Buyer objection to manifest error; add partial-COD/punch-list mechanics; consider a lower threshold or MW-pro-rata COD. |

### D-25  Termination damages formula and aggregate liability cap

| References | TS: No TS counterpart (TS §3.5, §7.3, §8.4 sole remedies) ¦ PPA: PPA §18.3(b); §16.2; §16.3 |
| --- | --- |
| Term Sheet | Liability for delay and underperformance limited to liquidated amounts. |
| Executed PPA | Termination damages = PV at 6% of (expected revenue for remaining Term at CQ × Contract Price) minus (market value of a replacement contract), “as reasonably determined by the non-defaulting Party”; aggregate liability cap equals total Term revenue (~$718M at formula prices). |
| Status / effect / severity | NEW TERM ¦ Adverse / ambiguous ¦ Medium ¦ Checklist Item(s) 12, 40 |
| Negotiation record | Not discussed. |
| Impact | The formula is one-directional and, as drafted, measures a Seller-side loss (contract value above market) even when Buyer is the non-defaulting Party — producing a nonsensical or disputable result in a Seller-default scenario; the non-defaulting Party’s unilateral determination of market value invites disputes. The liability cap provides no practical protection. |
| Recommendation | Replace with a symmetrical market-standard settlement amount (gains and losses, commercially reasonable quotations, Financing Party protections) and a meaningful Seller liability cap (e.g., tied to the performance bond amount or a fixed $/kW). |

## 4.4 Performance guarantees

### D-15  Minimum Annual Energy Production reduced to 75% of CQ (637,500 MWh)

| References | TS: TS §8.1 ¦ PPA: PPA §8.3; Ex. A (“MAEP”) |
| --- | --- |
| Term Sheet | 80% of CQ = 680,000 MWh. |
| Executed PPA | 75% of CQ = 637,500 MWh. |
| Status / effect / severity | AGREED ¦ Seller-favorable ¦ Low (documentation) ¦ Checklist Item(s) 12(ii) |
| Negotiation record | Agreed orally with Tamara Nouri and Howard Bledsoe in mid-January in exchange for Seller providing quarterly (rather than annual) generation reports; rationale: early-year production variability from wake effects of a neighboring wind farm that entered the planning picture after the Term Sheet. No TS amendment or side letter. |
| Impact | Legally effective: the PPA is a signed writing that supersedes the TS (PPA §20.3; TS §18.5), so the TS §18.6 written-amendment requirement is satisfied by the PPA itself and no TS amendment is needed. Diligence sensitivity: Ridgeline will view it as loosened performance discipline, and the stated rationale (new neighboring-wind-farm wake losses) must be reconciled with the independent engineer’s P50 of 876,000 MWh (Item 7), which may not yet reflect the new wake source. |
| Recommendation | Disclose as an agreed deviation with rationale; confirm IE report models the neighboring project’s wake; obtain written Buyer acknowledgment in the First Amendment recitals. |

### D-16  Shortfall LD rate reduced to 50% of Contract Price

| References | TS: TS §8.2–8.3 ¦ PPA: PPA §8.4 |
| --- | --- |
| Term Sheet | 75% of then-applicable Contract Price per MWh below 680,000 MWh. |
| Executed PPA | 50% of then-applicable Contract Price per MWh below 637,500 MWh. Illustration recomputes correctly: (637,500 – 600,000) × 50% × $38.50 = $721,875. |
| Status / effect / severity | AGREED ¦ Seller-favorable ¦ Low (documentation) ¦ Checklist Item(s) 12(ii) |
| Negotiation record | Same package as D-15; agreed verbally with Ms. Nouri and Mr. Bledsoe; Mr. Langdon’s January 15 markup confirmed it would be reflected. No side letter. |
| Impact | Example (CY1, 600,000 MWh adjusted output): TS terms 80,000 MWh × $28.875 = $2,310,000; PPA $721,875. At 670,000 MWh: TS $288,750; PPA $0. Ridgeline’s model and Elkhorn’s downside case should use the PPA terms. |
| Recommendation | Disclose as agreed; same documentation approach as D-15. |

### D-17  Quarterly generation reporting (consideration for D-15/D-16) not reflected

| References | TS: N/A (consideration for agreed deviations) ¦ PPA: PPA §3.4 (construction progress only), §7.3 (monthly meter data) |
| --- | --- |
| Term Sheet | N/A |
| Executed PPA | No quarterly generation report covenant. §3.4 quarterly reports cover construction only; §7.3 already requires monthly meter data reports and real-time access. |
| Status / effect / severity | DRAFTING (documentation gap) ¦ Neutral; evidentiary ¦ Low ¦ Checklist Item(s) 12(ii) |
| Negotiation record | Negotiation Summary §1 records the trade. |
| Impact | Absence of the agreed quid pro quo weakens the paper trail showing the 75%/50% terms were a bargained-for exchange and leaves room for Buyer to claim an unperformed side commitment. |
| Recommendation | Offer to add a quarterly operating report covenant in the First Amendment (low operational cost given §7.3) — useful goodwill currency. |

### D-12  Mechanical Availability LD rate $65,000 (not $50,000) per percentage point

| References | TS: TS §9.1–9.3 ¦ PPA: PPA §8.7; Ex. C §3 |
| --- | --- |
| Term Sheet | 95% guarantee; $50,000 per point (pro rata). Example: 93% → $100,000. |
| Executed PPA | 95% guarantee; $65,000 per point. Example: 93% → $130,000. Adds a no-double-recovery rule vs. Shortfall LDs (favorable). Methodology in Ex. C §3 is consistent with TS §1 exclusions. |
| Status / effect / severity | NOT AGREED ¦ Adverse ¦ Medium ¦ Checklist Item(s) 37, 12(ii) |
| Negotiation record | Negotiation Summary §2: rate “should carry forward unchanged.” Checklist Item 37 specifically flags this for review against $50,000. |
| Impact | +30% per point. The Nordex LTSA (Item 37) availability guarantee/LDs must back-to-back the PPA rate; a mismatch leaves Seller with unhedged exposure. |
| Recommendation | Restore $50,000 per point; conform the illustration. |

### D-13  20% annual LD cap no longer covers Availability LDs

| References | TS: TS §9.4 ¦ PPA: PPA §8.5, §8.7 |
| --- | --- |
| Term Sheet | Total aggregate LDs under §8 (Shortfall) and §9 (Availability) combined capped at 20% of annual revenue at CQ × Contract Price. |
| Executed PPA | §8.5 caps only “aggregate Shortfall LDs”; Availability LDs are outside the cap (subject only to the §16.3 aggregate-Term cap). |
| Status / effect / severity | NOT AGREED ¦ Adverse ¦ Medium ¦ Checklist Item(s) 12(ii), 40 |
| Negotiation record | Not discussed; Term Sheet position settled. |
| Impact | Theoretical uncapped Availability LD exposure (e.g., a fleet-wide serial defect) on top of a 20% Shortfall cap (~$6.5M in CY1). |
| Recommendation | Amend §8.5 to cap Shortfall LDs and Availability LDs combined at 20% of annual revenue, per TS §9.4. |

### D-14  Performance LDs no longer a clean sole remedy

| References | TS: TS §8.4 ¦ PPA: PPA §8.1 (last sentence), §8.5 |
| --- | --- |
| Term Sheet | Shortfall LDs are Buyer’s sole and exclusive remedy for failure to achieve MAEP, subject only to FM adjustment. |
| Executed PPA | Sole remedy “except for Buyer’s termination rights under Article 18 in the event of repeated material shortfalls constituting a material breach,” and §8.1 adds “Nothing in this Article 8 shall limit Buyer’s rights under any other provision.” |
| Status / effect / severity | NOT AGREED / NEW TERM ¦ Adverse ¦ Medium ¦ Checklist Item(s) 12(ii) |
| Negotiation record | Not discussed. |
| Impact | Opens a path to termination and §18.3(b) termination damages for underperformance, undermining the economic benefit of the agreed 75%/50% concession (D-15/D-16). “Repeated material shortfalls” is undefined. |
| Recommendation | Delete §8.1 last sentence; either delete the Article 18 carve-out or define an objective termination trigger (e.g., output below a stated % of MAEP in two consecutive CYs, net of FM/System Curtailment, after Financing Party cure). |

## 4.5 Force majeure, change of law and disputes

### D-8  Force majeure termination after 12 months (not 18), on 60 days’ notice

| References | TS: TS §14.4 ¦ PPA: PPA §12.4 |
| --- | --- |
| Term Sheet | Either Party may terminate if FM continues 18 continuous months and prevents a material portion of performance; 30 days’ notice, delivered no earlier than expiry of the 18 months. |
| Executed PPA | Either Party may terminate if FM continues 12 consecutive months, on 60 days’ notice; no “material portion of performance” qualifier. |
| Status / effect / severity | NOT AGREED ¦ Adverse ¦ High ¦ Checklist Item(s) 12(v) |
| Negotiation record | Negotiation Summary §2: the 18-month period “was important to us and we did not agree to shorten it.” |
| Impact | Shorter tail increases risk that a prolonged outage (e.g., a major tornado/ice event or interconnection failure) ends the offtake before insurance-funded repair is complete; business interruption cover is only 12 months (§15.1(f)). Lenders and tax equity size termination risk on this period. Loss of the materiality qualifier means a minor FM affecting a small obligation could support termination. |
| Recommendation | Restore 18 months, 30 days’ notice, and the “material portion” qualifier. |

### D-9  Force majeure definition and conditions narrowed

| References | TS: TS §14.1–14.3 ¦ PPA: PPA §12.1–12.3 |
| --- | --- |
| Term Sheet | Includes “equipment failure not attributable to the negligence of the affected Party” and “labor strikes or lockouts affecting the Project or critical suppliers”; grid emergencies; governmental actions. Prompt notice. |
| Executed PPA | Omits equipment failure; excludes strikes involving Seller’s own employees or contractors at the Facility; excludes “normal wear and tear or equipment degradation” and permit failures; FM relief conditioned on notice within 5 Business Days (§12.3). Adds denial/revocation of permits and SPP system failure (favorable). |
| Status / effect / severity | NOT AGREED ¦ Mixed, net adverse ¦ Medium ¦ Checklist Item(s) 12(v) |
| Negotiation record | Not discussed in Negotiation Summary. |
| Impact | Non-negligent serial defects or catastrophic component failures would no longer excuse performance; strict 5-BD notice creates a forfeiture trap. |
| Recommendation | Restore TS equipment-failure and labor language; change notice to “prompt” or “as soon as practicable, and in any event within 10 Business Days” without forfeiture. |

### D-10  Change of law: Buyer-bears-100% new transmission charges carve-out omitted

| References | TS: TS §13.1–13.2 ¦ PPA: PPA §14.1–14.2; §5.2; §5.3 |
| --- | --- |
| Term Sheet | Each Party bears own change-of-law costs, EXCEPT Buyer bears 100% of new transmission charges, access fees, ancillary charges or other transmission-related costs imposed on the Project or on delivery to the Delivery Point by any authority/RTO/SPP after execution. |
| Executed PPA | Generic “each Party bears its own increased costs” clause, triggered only by a “material increase” of >$500,000 per Contract Year, with non-binding good-faith renegotiation. No transmission carve-out. §5.2 puts all costs to deliver to the Delivery Point (including network upgrades and maintaining the LGIA) on Seller; §5.3 only allocates charges from the Delivery Point to Buyer’s load to Buyer. |
| Status / effect / severity | NOT AGREED ¦ Adverse ¦ High ¦ Checklist Item(s) 22, 12 |
| Negotiation record | Negotiation Summary §2: Mr. Langdon’s initial draft had the generic clause; Seller “pushed back” in its first comments and required the specific carve-out. The executed text is the initial draft position. |
| Impact | New SPP transmission/ancillary charges imposed on generators (a live SPP policy area) would fall on Seller for 20 years with no price relief — an unquantified, uncapped revenue risk that Ridgeline and Elkhorn will stress in the model (Items 22, 40). |
| Recommendation | Insert TS §13.2 verbatim as new §14.2(b), and make clear §5.2 does not allocate post-execution new transmission-related charges to Seller. |

### D-11  Dispute resolution: litigation in Osage County District Court instead of mediation + AAA arbitration

| References | TS: TS §17.1–17.5 ¦ PPA: PPA §19.1–19.4 |
| --- | --- |
| Term Sheet | Non-binding AAA mediation (Oklahoma City); then binding AAA Commercial arbitration, three arbitrators, seated in Oklahoma City, reasoned award; confidential; costs shared. |
| Executed PPA | 30-day executive negotiation; non-AAA mediation in Oklahoma City (60 days); then exclusive jurisdiction of the District Court of Osage County; no arbitration; no confidentiality of proceedings (only mediation statements); waiver of fee recovery. |
| Status / effect / severity | NOT AGREED ¦ Adverse ¦ High ¦ Checklist Item(s) 43, 12(vii) |
| Negotiation record | Negotiation Summary §2: Mr. Langdon’s first draft had Osage County litigation; Seller flagged it “as unacceptable” and believed he agreed to revert to arbitration. |
| Impact | Public proceedings in the Buyer’s home-county court, before local jurors, against a municipal utility serving the region; loss of confidentiality (which the Checklist notes is relevant to tax equity); no specialist tribunal for curtailment/SCADA measurement disputes (§6.3) or the Exhibit B pricing conflict. |
| Recommendation | Replace Article 19 with TS §17 (AAA mediation, three-arbitrator AAA arbitration seated in Oklahoma City, confidentiality per TS §17.4 including disclosure to Financing Parties). |

## 4.6 Credit support

### D-21  Performance bond due within 30 days of Effective Date (not 30 days before construction)

| References | TS: TS §11.1–11.2, §11.4 ¦ PPA: PPA §13.1; §2.4(a); Ex. F §2 |
| --- | --- |
| Term Sheet | $7.5M bond, surety rated ≥ A– (Atlas or equivalent NRSRO), posted no later than 30 days prior to commencement of construction. |
| Executed PPA | $7.5M bond, surety rated ≥ A– by Atlas Credit Services only, delivered within 30 days of the Effective Date (i.e., by March 6, 2025); effective from the Effective Date; failure is an Event of Default after 30 days’ notice (§18.1(c)). |
| Status / effect / severity | NOT AGREED ¦ Adverse ¦ Medium (urgent) ¦ Checklist Item(s) 16 |
| Negotiation record | Not discussed. |
| Impact | Checklist Item 16 shows Highpoint Surety & Hartleigh Co. rating confirmation still pending as of late February. If not delivered by March 6, 2025, Buyer can serve notice starting the 30-day clock to an Event of Default — weeks before close. Rating requirement narrowed to Atlas only (TS allowed equivalent rating from another agency). |
| Recommendation | Confirm bond delivery status immediately; if not delivered, either deliver now or obtain Buyer’s written extension; restore TS timing and “or equivalent rating” language in the First Amendment. |

### D-22  Bond step-down omitted; bond covers all obligations for full Term on demand

| References | TS: TS §11.3 ¦ PPA: PPA §13.1; Ex. F §§1–3 |
| --- | --- |
| Term Sheet | Full amount for first 5 Contract Years after COD, then reduced to $3,750,000 for remainder of Term (or other agreed schedule). |
| Executed PPA | Full $7.5M for the entire Term, renewable annually, with replacement within 30 days of surety downgrade; Ex. F guarantees “all” Seller obligations and is payable on Buyer’s certification of default, without exhaustion. |
| Status / effect / severity | NOT AGREED ¦ Adverse ¦ Medium ¦ Checklist Item(s) 16, 28 |
| Negotiation record | Not discussed. |
| Impact | Higher bonding cost and capacity usage for ~15 additional years at the full amount; on-demand certification feature behaves closer to a letter of credit and increases draw risk (e.g., in combination with D-7 and D-14). |
| Recommendation | Restore step-down to $3.75M after CY5; limit bond scope to Delay LDs, Shortfall/Availability LDs and termination payments as capped; require a final, non-appealable determination or a cure period before draw. |

### D-24  Buyer credit support conditional; downgrade collateral

| References | TS: TS §12.1–12.2 ¦ PPA: PPA §13.2, §13.3; §2.3(e) |
| --- | --- |
| Term Sheet | No Buyer credit support required. |
| Executed PPA | None required so long as Buyer keeps one investment-grade rating; if both agencies downgrade below investment grade, Seller may require 3 months’ expected revenue as cash collateral; MAC CP tied to sub-IG downgrade. |
| Status / effect / severity | NEW TERM ¦ Seller-favorable ¦ Low ¦ Checklist Item(s) 13 |
| Negotiation record | Not discussed. |
| Impact | Improves Seller/financing position; supports Item 13 Buyer credit analysis. |
| Recommendation | Disclose; no change needed. |

# 5. Observations on the Negotiation Record

Pattern. Four items Seller recorded as rejected or walked back in negotiations (80% curtailment compensation, Osage County litigation, the generic change-of-law clause, and a lender-only “Financing Party”) appear in the executed PPA in Buyer’s initial-draft form, and three items Seller said must carry over unchanged (Delay LDs, 18-month FM termination, $50,000 Availability LDs) were changed. This suggests that the near-final Prescott & Hale draft expected January 27–28 was executed on February 4 (two days before the TS §18.2 February 6 deadline) without a full tie-out against the Term Sheet. We should establish the drafting history (Langdon markups of January 15 and later, Seller comments, any execution-version redline) before engaging Buyer, because it determines how we frame the amendment request.

Legal leverage is limited. Because PPA §20.3 and TS §18.5 give the PPA priority, Seller’s realistic remedies are commercial (amendment) rather than legal. Reformation for mutual mistake is conceivable where Buyer’s counsel gave contrary assurances (D-1, D-5, D-11), but the evidence is Seller-side recollection, the clauses are unambiguous, and the forum would be Osage County District Court under the very clause in dispute; it is not a viable path to an April 15 close. The Term Sheet remains useful for D-4, where the PPA is internally ambiguous (§4.2(a) vs. §4.2(b)/§1.3).

Trading currency. (i) Correcting Exhibit B to 1.5% (worth ~$23.18M nominal to Buyer and something Buyer will want for its own audit and rate purposes); (ii) adding the agreed quarterly generation reports; (iii) confirming the excess-REC and early-COD items with clean mechanics. None of these costs Seller value it can realistically keep.

Agreed deviations do not need a Term Sheet amendment. Ms. Kowalski’s question is answered: the signed PPA supersedes the Term Sheet for the 75% MAEP and 50% Shortfall LD terms, and TS §18.6’s writing requirement is satisfied by the PPA itself. Ridgeline will nonetheless want to see Buyer’s acknowledgment; recite it in the First Amendment.

Authority and counterparty details. PPA signature block shows Ms. Kowalski signing for Seller as authorized signatory of Verdana as sole member; obtain the Verdana consent/incumbency for the closing set (Items 1–3, 45). Buyer Board of Trustees approval (TS §18.3(b); PPA §11.2(b), (g)) should be evidenced in the Prescott & Hale confirmation letter (Item 14), which is not started.

# 6. Financial Close Risk Assessment (Tax Equity DD Checklist)

Overall assessment: RED — financial close on April 15, 2025 is at high risk unless a First Amendment (or, for D-1/D-2 only, a Ridgeline-acceptable direct consent) is executed before close. The four Checklist items flagged “Requires Attention” (12, 18, 31, 43) all resolve adversely on the executed PPA. RAG reflects the PPA as executed, before remediation.

| Item | Checklist requirement | Finding on executed PPA | RAG | Required before close |
| --- | --- | --- | --- | --- |
| 12 | PPA consistent with TS in all material respects (pricing, escalation, PG, LDs, curtailment, FM, assignment, disputes, RECs) | Not consistent: 26 deviations; 2 agreed, 2 open-but-included, 22 not agreed, new or drafting; 2 Critical and 8 High (D-3 becomes Critical in combination with D-1). Sub-items (i)–(viii) all deviate. | RED | Deliver deviation report by Mar. 14; execute First Amendment; disclose agreed deviations (D-15, D-16, D-18, D-20) with rationale. |
| 18 | Consent-free collateral assignment to tax equity / partnership flip | Fails (a), (b); (c) consent required under §17.1(b) (not-unreasonably-withheld, but with Buyer conditions); Ex. H §8 expressly excludes tax equity (D-1, D-3). | RED | Amend Ex. A, §17.1, Ex. H; fix change-of-control and §11.1(g). Gating for Ridgeline IC. |
| 31 | Step-in, notice and cure rights for tax equity; Rev. Proc. 2007-65 consistency | Rights in §17.3/§18.4/Ex. H run only to lenders (D-2). Tax counsel to confirm safe-harbor implications. | RED | Same amendment; tax-equity-usable consent form; tax opinion (Item 39) dependent on cure. |
| 43 | Governing law Oklahoma; mediation + AAA arbitration in OKC | Governing law conforms (§20.1). Dispute resolution is Osage County litigation, non-confidential (D-11). | RED | Replace Article 19 with TS §17. |
| 15 | CQ 850,000 MWh; CY1 revenue $32,725,000; Ex. B matches 1.5% escalator | CQ and CY1 revenue conform; Ex. B table does not match (D-4). | AMBER | Correct Ex. B (Schedule 1). |
| 40 | Financial model uses correct 1.5% escalation; reflects curtailment, PG and LD exposure | Model must use formula, not Ex. B; reflect 80% curtailment (unless fixed), 75%/50% PG, $175k/$2.5M Delay LDs, $65k Availability LDs outside cap, generic CoL. | AMBER | Ridgeline to run on formula prices and post-amendment terms; sensitivity for unremedied items. |
| 22 | Buyer bears 100% of new transmission charges | Carve-out omitted; Seller bears risk (D-10). | RED | Insert TS §13.2. |
| 16 | $7.5M bond from surety rated ≥ A– (Atlas) | Amount and rating conform; due by Mar. 6, 2025; no step-down; on-demand form (D-21, D-22). Highpoint rating confirmation pending. | AMBER | Confirm delivery/extension now; restore step-down. |
| 37 | Availability LD rate vs. TS $50,000/ppt | $65,000/ppt and outside 20% cap (D-12, D-13). | AMBER | Restore $50,000 and combined cap; align Nordex LTSA. |
| 34 / 36 | Schedule alignment with Ex. G; COD testing protocol aligned to PPA | Dates conform (Early COD Mar. 1, 2026; Expected June 1, 2026; GCOD Sept. 1, 2026; Outside Sept. 1, 2027) but Outside Date mechanics differ (D-7) and COD test is 240 MW with Buyer review (D-23). Item 34 notes cite Outside Date “per term sheet” — consequences now differ. | AMBER | Build Item 36 protocol to §3.2; seek D-7/D-23 fixes. |
| 30 / 29 | Elkhorn to execute Ex. H Lender Consent; intercreditor | Ex. H usable by Elkhorn as lender Agent but contains anti-tax-equity §8; intercreditor will be distorted until Ridgeline has parity (D-2). | AMBER | Revise Ex. H before Elkhorn review. |
| 2 / 19 / 45 | LLC Agreement restatement for flip; flip operating agreement; bring-down | Admitting Ridgeline conflicts with §11.1(g) and possibly §17.1(b) (D-3). | RED | Amend §11.1(g)/§17.1(b) before LLC restatement. |
| 13 | Buyer credit; no Buyer credit support | Conforms; PPA adds downgrade collateral (D-24, favorable). | GREEN | None. |
| 14 | Buyer counsel authorization/enforceability letter | Not started; also needed to evidence Board approval of the amendment. | AMBER | Request now from Prescott & Hale (200 East Broadway, Suite 800). |
| 44 | CP checklist; deviation report gating for Ridgeline IC | Deviation report is gating; amendment execution should be a closing CP. | AMBER | Add First Amendment and revised Ex. H consents as CPs. |

## Quantified exposure (selected, at Contract Quantity)

| Item | Term Sheet | Executed PPA | Difference |
| --- | --- | --- | --- |
| Exhibit B pricing, CY6–20 revenue (D-4) | $717.73M total Term revenue (formula) | $740.91M if table enforced | +$23.18M nominal / +$9.58M PV@6% (unbankable; dispute risk) |
| Economic curtailment comp. at 42,500 MWh cap (D-5) | $1,472,625 (CY1) | $1,309,000 (CY1) | –$163,625/yr in CY1; ~–$3.59M over Term |
| Delay LDs, 12-month delay (D-6) | $1,500,000 (cap) | $2,100,000 | +$600,000; max +$1.0M (cap $2.5M) |
| Availability LDs at 93% (D-12) | $100,000 | $130,000 | +$30,000 per year; uncapped by 20% cap (D-13) |
| Shortfall LDs at 600,000 MWh adjusted output, CY1 (D-15/16) | $2,310,000 | $721,875 | –$1,588,125 (agreed, Seller-favorable) |
| Shortfall LDs at 670,000 MWh (Negotiation Summary example) | $288,750 | $0 | –$288,750 (agreed) |
| Bond amount after CY5 (D-22) | $3,750,000 | $7,500,000 | +$3.75M bonded for CY6–20 |

# 7. Remediation Plan and Timeline

Proposed First Amendment to PPA (single package), in priority order:

Financing Party / tax equity: amend Ex. A, §§17.1(a), 17.3, 18.4, 20.9; revise Ex. H (remove §8 tax equity exclusion; tax-equity-usable form); reinstate “no cost to Buyer” and “material covenant” (D-1, D-2).

Ownership: restore TS §15.3 change-of-control notice regime; carve out tax equity admission, flips and Financing Party enforcement; conform §11.1(g) (D-3, D-26).

Pricing: replace Ex. B Parts 2–3 with formula prices (Schedule 1); make formula control (D-4).

Restore Term Sheet economics: 90% curtailment (D-5); $125,000/month and $1.5M Delay LD cap (D-6); $50,000 Availability LDs and combined 20% cap (D-12, D-13); 18-month FM termination (D-8); TS §13.2 transmission carve-out (D-10); TS §17 arbitration (D-11).

Remedies: delete §18.1(a) and §8.1 last sentence / repeated-shortfall termination, restore sole-remedy construct, fix termination damages formula, add FM extension of GCOD/Outside Date (D-7, D-14, D-25).

Credit support: TS bond timing, step-down to $3.75M after CY5, narrower draw conditions (D-21, D-22).

Confirmations: Buyer acknowledgment of agreed deviations (D-15, D-16), early COD (D-20) and excess RECs with mechanics (D-18); add quarterly generation reports (D-17); fix ancillary errors (Section 8).

Timeline (working back from April 15, 2025):

| Date | Action | Owner |
| --- | --- | --- |
| Immediately | Confirm performance bond delivered by Mar. 6, 2025 (or obtain Buyer extension). Pull drafting history (Langdon Jan. 15 markup, Seller comments, execution version). | T&M (R. Matsuda) / Verdana |
| By Mar. 7, 2025 | Send First Amendment draft and issues list to Prescott & Hale; request Buyer Board scheduling; request Item 14 counsel letter. | T&M (C. Ainsworth) |
| By Mar. 14, 2025 | Deliver Ridgeline-facing deviation report with remediation plan; walk Priya Venkataraman through D-15/D-16 rationale; confirm whether a direct Ridgeline consent is an acceptable fallback for D-1/D-2. | T&M / Verdana (D. Kowalski) |
| Mar. 17–Apr. 4, 2025 | Negotiate amendment; Buyer Board of Trustees approval (public meeting notice lead time to be confirmed); share revised Ex. H with Elkhorn. | T&M / Buyer |
| By Apr. 11, 2025 | Execute First Amendment; Buyer executes Lender Consent (Elkhorn) and tax equity consent (Ridgeline); Ridgeline model and tax opinion updated. | All |
| Apr. 15, 2025 | Financial close (amendment and consents as CPs). | All |

If Buyer will not amend before April 15, the minimum close-enabling package is: (1) a Buyer consent and estoppel in favor of Ridgeline granting §17.3 rights and confirming that admission of Ridgeline and any flip are not a change of control or breach of §11.1(g); and (2) a signed side letter correcting Exhibit B to the formula. All other items would then be disclosed as accepted deviations, priced into the model, and carried as post-closing covenants — subject to Ridgeline and Elkhorn agreement.

# 8. Ancillary Inconsistencies and Clean-up Items

| Ref. | Issue | Comment |
| --- | --- | --- |
| Ex. C §1; Recitals | Installed capacity 62 × 4.0 MW = 248 MW vs. 250 MW nameplate | Ex. C attributes the gap to “turbine optimization features” and possible reserve-pad turbines. Relevant to COD 240 MW test (D-23), P50 basis and PTC/IE review (Items 6, 7). |
| Ex. C §1 vs. TS §2 | Site described as ~12 miles NW of Pawhuska (PPA) vs. ~22 miles (TS) | Confirm with survey/title (Items 10, 11). |
| Ex. C §1 | Site within Osage Nation; Osage Minerals Council/BIA approvals “obtained or in the process of being obtained” | Not in TS; confirm status for permits CP (§2.3(a)) and Item 23. |
| §20.2 vs. TS preamble / Negotiation Summary | Seller notice contact: dkowalski@crescentridgewind.com, (405) 555-4218 vs. dkowalski@verdanarenewable.com, (405) 553-2180; T&M at 4400 Meridian Tower Suite 1200 vs. TS 100 North Broadway Ave., Suite 2800; Prescott & Hale at 200 East Broadway, Suite 800 vs. TS 412 East 6th Ave., Suite 300 | Confirm correct notice details; notice errors can defeat default/cure notices. Checklist Item 14 uses the PPA address for Prescott & Hale. |
| TS Annex A | Annex A prices deviate by $0.01–$0.02 from the TS §5.4 formula in CY7 and CY9–20 | Formula governs (TS §5.4, §5.6 “indicative”); use formula values in amendment. |
| Ex. B Part 3 | CY6 sample revenue $33,379,500 uses erroneous $39.27 | Replace with $33,218,000. |
| Ex. G | Table formatting broken (Notice to Proceed row outside table) | Clean up in amendment. |
| §2.2 | Term “commences on the Effective Date” and runs 20 Contract Years after COD (TS: 20 years from COD) | Economically consistent; pre-COD period is additional. No action. |
| §10.4 | Tax credits (PTC/ITC) retained by Seller | Conforms with structure; confirm for Item 20. |
| Checklist Item 17 | Notes say TS binding “subject to execution of definitive PPA within 90 days (extended by mutual consent)” | PPA was executed Feb. 4, 2025, within the Feb. 6 deadline; no extension appears necessary — correct the checklist note. |
| Checklist Item 26 | Lists only CGL $5M, pollution $2M, builder’s risk | PPA Art. 15 / Ex. E also require WC/EL, operational property, BI (12 months), auto ($2M) and umbrella ($10M) cover; Ridgeline as additional insured not required by PPA (Item 27). |

# Schedule 1 — Contract Price Tie-Out (Term Sheet formula vs. Annex A vs. PPA Exhibit B)

| CY | Formula (1.5%) | TS Annex A | PPA Ex. B | Ex. B – Formula | Revenue effect at 850,000 MWh |
| --- | --- | --- | --- | --- | --- |
| 1 | $38.50 | $38.50 | $38.50 | — | — |
| 2 | $38.50 | $38.50 | $38.50 | — | — |
| 3 | $38.50 | $38.50 | $38.50 | — | — |
| 4 | $38.50 | $38.50 | $38.50 | — | — |
| 5 | $38.50 | $38.50 | $38.50 | — | — |
| 6 | $39.08 | $39.08 | $39.27 | +$0.19 | +$161,500 |
| 7 | $39.66 | $39.67 | $40.06 | +$0.40 | +$340,000 |
| 8 | $40.26 | $40.26 | $40.86 | +$0.60 | +$510,000 |
| 9 | $40.86 | $40.87 | $41.68 | +$0.82 | +$697,000 |
| 10 | $41.48 | $41.46 | $42.51 | +$1.03 | +$875,500 |
| 11 | $42.10 | $42.08 | $43.36 | +$1.26 | +$1,071,000 |
| 12 | $42.73 | $42.71 | $44.23 | +$1.50 | +$1,275,000 |
| 13 | $43.37 | $43.35 | $45.11 | +$1.74 | +$1,479,000 |
| 14 | $44.02 | $44.00 | $46.02 | +$2.00 | +$1,700,000 |
| 15 | $44.68 | $44.66 | $46.94 | +$2.26 | +$1,921,000 |
| 16 | $45.35 | $45.33 | $47.87 | +$2.52 | +$2,142,000 |
| 17 | $46.03 | $46.01 | $48.83 | +$2.80 | +$2,380,000 |
| 18 | $46.72 | $46.70 | $49.81 | +$3.09 | +$2,626,500 |
| 19 | $47.42 | $47.40 | $50.81 | +$3.39 | +$2,881,500 |
| 20 | $48.13 | $48.11 | $51.80 | +$3.67 | +$3,119,500 |
| Total |  |  |  |  | +$23,179,500 |

Formula: P(N) = $38.50 × 1.015^(N–5) for N ≥ 6, rounded to the nearest cent (TS §5.4; PPA §4.2(b)). Exhibit B values match a 2.0% compounding escalator rounded year-on-year for CY6–13 and CY16–19, with further deviations in CY14 ($46.02 vs. $46.01), CY15 ($46.94 vs. $46.93) and CY20 ($51.80 vs. $51.83 on a 2.0% basis). PV of the overstatement at 6% (annual, end-of-year from COD): ~$9.58M.

# Schedule 2 — Open Questions for Client / Prescott & Hale

Did Seller review an execution-version redline against the Term Sheet before February 4? Obtain all Langdon markups (including January 15) and Seller comment sets.

Was the excess-REC retention (D-18) and March 1, 2026 early COD (D-20) expressly agreed with Ms. Nouri/Mr. Bledsoe before execution, and by whom?

Has the $7.5M Highpoint Surety bond been delivered (due March 6, 2025), and is the A– Atlas rating confirmed?

Does the independent engineer’s P50 (876,000 MWh) reflect the neighboring wind farm’s wake effects cited as the rationale for D-15?

Will Ridgeline accept a direct Buyer consent (rather than a definitional amendment) as a fallback for D-1/D-2, and what does Ridgeline’s tax counsel require under Rev. Proc. 2007-65 (as modified)?

What is the Buyer Board of Trustees meeting calendar and public notice lead time for approving an amendment before April 15?

Does the Nordex LTSA availability guarantee back-to-back the PPA’s 95% / $65,000 (or restored $50,000) regime and the 240 MW COD test?

Prepared on the basis of the four documents listed in Section 2 only; no independent verification of facts outside those documents. Figures are computed at the Contract Quantity for comparison purposes and are not forecasts.